## Project Data
Project Name | ...
Online team meeting | https://fau.zoom-x.de/j/3913240515?pwd=TWo2NkZmaVZFWDVKckNKVzQyRG4zdz09
Production system (if any) | TBT
Test system (if any) | TBT
GitHub repository | https://github.com/amosproj/amos2025ws01-opensearch-load-tester
GitHub feature board | https://github.com/orgs/amosproj/projects/89/views/2
GitHub imp-squared backlog | https://github.com/orgs/amosproj/projects/93/views/1
Team T-shirt (white) | https://www.shirtinator.de/en/s/nasAq-u7RjO3FQ4BPPUSLw
Team T-shirt (black) | https://www.shirtinator.de/en/s/0VuwTYIwRviJfsV7ERwamA
Additional materials | ...
Team maling list | oss-amos-proj1@lists.fau.de

## Project Team
Last Name | First Name | GitHub User Name | Email Address
Lorenz | Alexander | Hydraneut | alexander.lorenz@fau.de
Buchner | Lea | LeaBuchner | lea.buchner@fau.de
Engelhard | Dirk | engelharddirk | dirk.engelhard@fau.de
Strachwitz | Carlo | Carlit0 | carlostrachwitz@gmail.com
Belz | Sara | SaraBelz | sara.belz@fau.de
Becker | Eugen | BeEugen | eugen.becker@fau.de
Hofmann | Leo | Leolingio | leohof23@gmail.com
Knecht | Sebastian | SeboKnt | sebastian.knecht@fau.de

## Role Assignments
Product Owner
# | Meeting Day | Review | Planning | Software Developer | Release Manager | Review assistant | Scrum Master | Comment
1 | 2025-10-15 | both | both | Everyone else | N/A | N/A | Alexander Lorenz
2 | 2025-10-22 | Lea Buchner | Dirk Engelhard | Everyone else | N/A | N/A | Alexander Lorenz
3 | 2025-10-29 | Dirk Engelhard | Lea Buchner | Everyone else | Carlo Strachwitz | N/A | Alexander Lorenz
4 | 2025-11-05 | Lea Buchner | Dirk Engelhard | Everyone else | Carlo Strachwitz | N/A | Alexander Lorenz | Build process review
5 | 2025-11-12 | Dirk Engelhard | Lea Buchner | Everyone else | Leo Hofmann | N/A | Alexander Lorenz
6 | 2025-11-19 | Lea Buchner | Dirk Engelhard | Everyone else | Sara Belz | N/A | Alexander Lorenz
7 | 2025-11-26 | Dirk Engelhard | Lea Buchner | Everyone else | Sebastian Knecht | N/A | Alexander Lorenz | Mid-term due
8 | 2025-12-03 | Lea Buchner | Dirk Engelhard | Everyone else | Eugen Becker | N/A | Alexander Lorenz
9 | 2025-12-10 | Dirk Engelhard | Lea Buchner | Everyone else | Eugen Becker | N/A | Alexander Lorenz
10 | 2025-12-17 | Lea Buchner | Dirk Engelhard | Everyone else | Leo Hofmann | N/A | Alexander Lorenz | Team Workshop
11 | 2026-01-07 | Dirk Engelhard | Lea Buchner | Everyone else | Sara Belz | N/A | Alexander Lorenz | No class but team meeting
12 | 2026-01-14 | Lea Buchner | Dirk Engelhard | Everyone else | Sebastian Knecht | Leo Hofmann | Alexander Lorenz
13 | 2026-01-21 | Dirk Engelhard | Lea Buchner | Everyone else | Leo Hofmann |  | Alexander Lorenz
14 | 2026-01-28 | Lea Buchner | Dirk Engelhard | Everyone else | Sara Belz |  | Alexander Lorenz
15 | 2026-02-04 | Dirk Engelhard | Lea Buchner | Everyone else | Sebastian Knecht |  | Alexander Lorenz | Demo day!+retrospective
Product owners, software developers, and Scurm Master are set and ideally don't change over time; the critical part is the Release Manager role you need to define here
Formulas:
Meeting Day = [Meeting Day, row above]+7

## Team Contract
Goals | achieve the project goal
get inside into the scrum and agile process
improve practical development skills
create something worth using
Meeting norms | everybody should feel safe
be punctual
Absence from meetings should be (if possible) declared a day in advance
Working norms | open door policy (everybody should be allowed to do mistakes)
maintaining good documentation
Backlog items are assigned by the developers themselve before they work (outside the team meeting)
Coordination norms | every Backlog item has at least 1 deticated person (if work has already started on it)
Contributers assigne them self to bakclog items
Communication norms | meetings take place in english unless stated otherwise
stick to the topic of the channel
We use discord as our primary method of communication
we check discord at least once a day (and react if needed)
We use Whatsapp for urgent communication (less than an hour)
Consideration norms | If you see something say something
We decide with majority vote
If we think we could help we extend it
Cont. improvement norms | constructive feedback is always welcome
We jointly review the happiness index
Rewards | celebrate successes
Appreciation and praise
Sanctions | apoligize sincerly
and find a funny way to apoligize
Signatures
Scrum Master | Alexander Lorenz
Product owner | Dirk Engelhard
Product owner | Lea Buchner
Software developer | Leo Hofmann
Software developer | Eugen Becker
Software developer | Sebastian Knecht
Software developer | Sara Belz
Software developer | Carlo Strachwitz

## Product Goal
Product Vision | Project Mission
Make OpenSearch deployments predictable, right-sized, and resilient by providing a standard, evidence-based benchmarking and load-testing platform that reveals real-world limits and behaviors. | Build a modular, extensible load-tester that reliably measures OpenSearch performance limits and produces reproducible artifacts for capacity planning and reliability engineering.

## Product Glossary
Term | Definition
OpenSearch | A search and analytics engine (Elasticsearch fork). In this project, OpenSearch is the target system for load and ingest testing.
Load Generator / load-generator | Component that produces requests/load against OpenSearch to perform performance and stress tests. Located in the load-generator module.
Load Test | A planned execution that runs a certain number of queries, a load pattern, or a duration against OpenSearch to measure behavior, throughput and latency.
Load Runner / LoadRunnerService | Service component that orchestrates query execution for a test (scheduling, threads, rate limiting, metric collection).
Query (Search Query) | A single search or aggregation request, represented as a JSON template under src/main/resources/queries/ (e.g. q1_ano_payroll_range.json). Templates may include parameters/placeholders.
Query Template | JSON template for a query with placeholders to be filled at runtime.
QueryRunRequest | DTO describing a request to run a query in the load generator (which query, repetitions, rate, etc.). Found in controller/QueryRunRequest.java.
Query Execution / QueryExecution | Abstraction for executing a query against a target. Implementations perform the actual call (or a no-op for dry runs).
OpenSearchQueryExecution | Concrete QueryExecution implementation that sends requests to OpenSearch.
NoOpQueryExecution | A test or dry-run implementation of QueryExecution that does not send real requests.
QueryExecutionFactory | Factory producing appropriate QueryExecution instances depending on configuration or target.
QueryRegistry | Registry or catalog of available query templates and metadata (names, paths, parameters).
Index | OpenSearch index: a logical collection of documents defined by mappings.
Document | A single JSON record stored in an index. Test data is created and indexed as documents.
Mapping | Schema-definition for an index (fields and types).
Aggregation | OpenSearch operation to group or summarize data (counts, sums, bucket aggregations). Examples: q5_ano_clients_aggregation.json.
Range Query | A query that filters documents based on numeric or date ranges (e.g., payroll ranges).
Match / Term Query | Full-text or exact-match queries in OpenSearch.
Bulk API / Bulk Indexing | Mechanism for inserting many documents in a single request to increase throughput.
Ingestion Rate | Number of documents indexed per time unit.
Throughput | Number of successfully processed requests per second (often QPS).
QPS (Queries Per Second) | Metric indicating how many queries are executed per second.
Concurrency | Number of parallel requests/threads during a test.
Latency | Time between request and response. Typical metrics: average, p95, p99.
Response Time | General term for latency; often reported with distribution statistics.
Error Rate | Fraction of failed responses (HTTP errors, timeouts) out of total requests.
Metrics Collector / metrics-reporter | Component that gathers runtime metrics (latency, throughput, errors) and exports or stores them. See metrics-reporter module.
MetricsCollectorService | Service in load-generator that aggregates metrics from test runs and forwards them to a reporter or sink.
Test Data | Data that is indexed into OpenSearch for testing, often generated synthetically (see testdata-generator).
testdata-generator | Module responsible for generating and optionally storing test datasets (models: AnoRecord, DuoRecord).
Ano / AnoRecord | Domain model class in the testdata-generator module. Represents a specific record schema used by some queries (fields defined in the model file).
Duo / DuoRecord | Another domain model in testdata-generator with a different schema; used by queries referencing duo data.
Recordable | Interface/abstraction implemented by AnoRecord and DuoRecord to provide serialization or indexing behavior.
PersistentDataGeneratorService | Service that persists generated test data (e.g., to files or external storage).
DynamicDataGeneratorService | Service that generates test data dynamically at runtime (randomized or parameterized fields).
FileStorageService | Utility/service for reading and writing generated test data to/from files.
OpenSearchDataService | Component that communicates with OpenSearch to index, delete, or query data.
Client (business entity) | Business object representing a customer/client. Queries like q7_duo_client_by_customer_number.json reference client data.
Booking | Business domain entity (e.g., a financial booking or reservation). Appears in queries like q4_duo_booking_by_client_and_state.json.
SLA (Service Level Agreement) - general concept | Target or acceptance values for latency/throughput/error rates used to validate system behavior under load.
Dry-run | Mode where queries are not actually sent to OpenSearch (see NoOpQueryExecution).
Warmup | Pre-measurement phase in load tests to warm caches and stabilize the system before capturing metrics.
Backpressure | System behavior when the target cannot keep up with the requested throughput; relevant to error rates and latency spikes.

## Sprint Goals
Sprint # | Sprint goal
1 | None
2 | None
3 | None
4 | Optional
5 | Internal component integration of each service
6 | First End-To-End test run
7 | Add Warm-Up and Ramp-Up Phase
8 | Query capabilities
9 | Query randomization
10 | Test insights and timeout handling
11 | Visualization preparation
12 | Visualization for demo
13 | Stabilization, tuning, packaging
14 | DEMO-DAY readiness

## Velocity Tracking
Sprint # | Story Points Realized | Avg
1 | 15 | 18.8
2 | 21 | 18.8
3 | 17 | 18.8
4 | 19 | 18.8
5 | 16 | 18.8
6 | 19 | 18.8
7 | 25 | 18.8
8 | 30 | 18.8
9 | 13 | 18.8
10 | 13 | 18.8
11 |  | 18.8
12 |  | 18.8
13 |  | 18.8
14 |  | 18.8
15 |  | 18.8
PLEASE CREATE THE VELOCITY CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Velocity Chart
Average Speed: | 18.8 | Points/Sprint
Scrum Master Tables
Sprint | Storypoints Planned | Storypoints Realized | Average Planned | Average Realized
1 | 10 | 15 | 19.5 | 18.8
2 | 23 | 21 | 19.5 | 18.8
3 | 18 | 17 | 19.5 | 18.8
4 | 19 | 19 | 19.5 | 18.8
5 | 21 | 16 | 19.5 | 18.8
6 | 19 | 19 | 19.5 | 18.8
7 | 31 | 25 | 19.5 | 18.8
8 | 26 | 30 | 19.5 | 18.8
9 | 23 | 13 | 19.5 | 18.8
10 | 24 | 13 | 19.5 | 18.8
11 | 7 |  | 19.5 | 18.8
12 | 18 |  | 19.5 | 18.8
13 | 16 |  | 19.5 | 18.8
14 | 18 |  | 19.5 | 18.8

## Mid-Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 110 | 110
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
1 | Deliver first increment of initialized software modules and an architecture plan |  | 10 | 110 | 15 | 110
2 | Deliver increment with Build process implementation and first module prototypes |  | 23 | 100 | 21 | 95
3 | Deliver increment with broad prototype implementation coverage |  | 18 | 77 | 17 | 74
4 | Deliver increment with first component integrations implemented |  | 19 | 59 | 19 | 57
5 | Deliver increment with more integration and technical test running capability |  | 21 | 40 | 16 | 38
6 | Deliver Increment with simple full test run routine executable |  | 19 | 19 | 19 | 22
7
Features
1 | Deliver first increment of initialized software modules and an architecture plan
|  | Research - OpenSearch | 3 |  | 3
|  | Research - Understand DATEV Data Structure (Industry Partner Input) for Load Tester Query Design | 1 |  | 1
|  | Developer Environment Setup | 1 |  | 1
|  | GitHub Repository Management Decision |  |  | 2
|  | Architecture evaluation/decision | 2 |  | 5
|  | Design Team Shirt | 1 |  | 1
Initialize SBOM
|  | Minimal Module Initialization | 2 |  | 2
2 | Deliver increment with Build process implementation and first module prototypes
|  | Define Representative Query Scenarios | 5 |  | 3
|  | Prepare Build Process Review | 2 |  | 2
|  | Research - Benchmark Tools for OpenSearch Load Tester | 3 |  | 3
|  | OpenSearchClient prototype | 3 |  | 3
|  | Build Process Decision | 2 |  | 2
|  | Data Generation Prototype | 3 |  | 3
|  | Architecture adaptation | 2 |  | 2
|  | Build Process Implementation | 2 |  | 2
|  | Github Signoff/Co-Author Automation | 1 |  | 1
3 | Deliver increment with broad prototype implementation coverage
|  | MetricsCollector Prototype Implementation | 5 |  | 3
|  | QueryExecution Prototypee Implementation | 3 |  | 2
|  | LoadRunner Component Prototype Implementation | 2 |  | 2
|  | Logging Mechanism Implementation | 2 |  | 2
|  | Data Generation <> OpenSearch Client Integration | 3 |  | 5
|  | Environment Variable Support for Dockerized Services | 2 |  | 2
|  | Automatic Shutdown of Testdata Generator Service | 1 |  | 1
4 | Deliver increment with first component integrations implemented
|  | MetricsCollector Prototype Implementation | 5 |  | 3
|  | QueryExecution Prototype Implementation | 3 |  | 2
|  | LoadRunner Component Prototype Implementation | 2 |  | 2
|  | Data Generation with OpenSearch Client Integration | 3 |  | 5
|  | Logging Mechanism Implementation | 2 |  | 2
|  | Implementation of Batch Processing for Data Pre-Loading | 3
|  | Unified Code Styling & Editor Configurations | 1 |  | 2
|  | Ano/Duo Separation | 3 |  | 3
5 | Deliver Increment with internal component integrations broadly implemented
|  | Load Generator Port Setup Dockerized Services | 3 |  | 2
|  | Load Generator Internal Component Integration | 5 |  | 5
|  | ReportController Component Prototype Implementation | 5 |  | 3
|  | Build Process Video | 2 |  | 2
|  | Definition of Done | 3 |  | 2
|  | Implementation of MetricsReporterClient Prototype | 3 |  | 2
6 | Deliver Increment with simple full test run routine executable
|  | Implementation of Load Test Scenario | 5 |  | 5
|  | Implementation of Batch Processing for Data Pre-Loading | 3 |  | 3
|  | ReportCreator Component Prototype Implementation | 5 |  | 8
|  | Wiki Creation | 3 |  | 3
|  | CI/CD Pipeline Setup | 3

## Mid-Project Burndown Chart
Development Speed: | 18.8 | Points/Sprint

## Final Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 163 | 163
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
7 | Deliver Increment with full test run executable supporting warm-up and synchronized load start |  | 31 | 163 | 25 | 163
8 | Deliver Increment with impoved query capabilities |  | 26 | 132 | 30 | 138
9 | Deliver Increment with broad query randomization |  | 23 | 106 | 13 | 108
10 | Deliver Increment with more test result insights |  | 24 | 83 | 13 | 95
11 | Deliver Increment with first data visualization steps |  | 7 | 59
12 | Deliver Increment with a data report visualization for demo purposes |  | 18 | 52
13 | Deliver Increment with Stabilization, tuning, packaging |  | 16 | 34
14 | Deliver Increment with finished, DEMO-DAY-Ready product |  | 18 | 18
Features
7 | Deliver Increment with full test run executable supporting warm-up and synchronized load start
|  | Complex Queries | 3
|  | Big Data Handling in MetricsReporter | 5 |  | 5
|  | Code Refactoring | 5 |  | 5
|  | Shared Library Creation | 1 |  | 1
|  | Configurable Queries per Second | 3 |  | 5
|  | Load Generator Request Synchronization | 5
|  | Optimize Random Generation of Test Data | 3 |  | 3
|  | Configurable Test Duration | 3 |  | 3
|  | Load Generator functionality Definition | 3 |  | 3
8 | Deliver Increment with impoved query capabilities
|  | Redesign Metrics Data Model | 2 |  | 2
|  | Extend Ano and Duo Index Mapping and Settings | 3 |  | 3
|  | Refactoring: Include DTO changes in Metrics Reporter | 2 |  | 2
|  | Query Parameter Randomization | 5 |  | 3
|  | Warm-Up Phase | 1 |  | 1
|  | Implementation of Batch Processing for Data Pre-Loading | 3 |  | 3
|  | Extend (Unit) Test Coverage | 5 |  | 5
|  | Test ending wait mechanism | 2 |  | 3
|  | CI/CD Pipeline Setup | 2 |  | 3
|  | Complex Queries | 2 |  | 5
9 | Deliver Increment with broad query randomization
|  | Load Generator Query Type Mix | 3 |  | 2
|  | Merge open PRs | 2 |  | 2
|  | Compound Queries | 5 |  | 1
|  | Leaf Queries: specialized/span queries | 5 |  | 3
|  | Expensive Queries | 5
|  | Global Load Test Start Synchronization | 3 |  | 5
10 | Deliver Increment with more test result insights
|  | Fix Queries getting lost without warning | 3
|  | Terminate Metrix Reporter after Report Generation | 1 |  | 2
|  | Loki interaction | 3 |  | 2
|  | Leaf Queries: specialized/span queries | 2 |  | 3
|  | Bug: Duration/QPS division by 0 Exception | 1 |  | 1
|  | Load Generator: add handling big data | 5
|  | Setup Grafana Dev Container | 2 |  | 1
|  | Loki setup/research | 2 |  | 1
|  | Grafana Input research | 3 |  | 1
|  | Introduce parent POM for centralized dependency & plugin management | 2 |  | 2
11 | Deliver Increment with first data visualization steps
|  | Grafana: Dashboard Creation | 3 |  | 3
|  | Execution of Multiple Test Runs | 2 |  | 2
|  | Research Open Search regarding performance | 2 |  | 2
|  | Query Timeout Handling | 3 |  | 8
|  | Fix Queries getting lost without warning | 3 |  | 5
|  | Load Generator add handling big data | 5 |  | 8
12 | Deliver Increment: Data report visualization for demo
|  | Double check metrics reporter cean behavior (output files, memory) | 3
|  | Architecture (Diagram) Refactoring | 3
|  | Configurable Query Type Distribution | 5
|  | Remove CSV output format | 3
|  | Metrics Reporter Error Behavior | 3
|  | Container Termination | 2
|  | Suppress noisy logs in Dashboard | 2
|  | Simple UI for loadtest start | 5
13 | Deliver Increment: Stabilization, tuning, packaging
|  | Update/Extend Documentation | 5
|  | SBOM Update | 3
|  | Demo Day Video Creation | 3
|  | Container Termination | 5
|  | Documentation Cleanup | 2
|  | Create custom scenario | 5
14 | Deliver Increment with finished, DEMO-DAY-Ready product
|  | Final Demo Workflow | 3
|  | Polished Dashboard & UX | 5
|  | Scenario Library Complete | 3
|  | Full System QA | 5
|  | Presentation + Demo Script | 5

## Final Project Burndown Chart
Avg. development speed (across all sprints): | 18.8 | Points/Sprint

## Definition of Done
# | Feature Definition of Done | Sprint Release Definition of Done | Project Release Definition of Done
Overview | A single new feature or user story implemented in Trunk Load (e.g., new query type, new CLI option, new scenario). | The subset of functionality and artifacts that must be finished and deliverable at the end of a sprint (sprint-level deliverable). | The final project release: full handover of the stress‑testing toolset, reproducible scenarios, baselines and deliverables.
Scope | Code, tests and docs needed to implement the feature in load-generator, metrics-reporter or testdata-generator. | All features/bugfixes scoped to the sprint board’s “Done” column, plus required scenarios and deliverables in Deliverables/sprint-XX/. | All features and fixes required for the final deliverable, automated scenarios (ramp, steady, spike, soak, chaos), reporting assets and reproducibility instructions in Deliverables/.
Acceptance Criteria | - Implements the story’s acceptance criteria from the issue. - At least one concrete example scenario demonstrating the feature exists. - No secrets added and no new critical static-analysis findings. - Excludes wide refactors unless explicitly requested. - Code compiles without errors locally and in CI. - Formatting and linting checks pass. - Minimal unit tests cover the relevant logic. - Code is documented where appropriate (Wiki/internal README). | - All sprint issues marked Done have merged PRs. - Each merged item satisfies its Feature or Bugfix DoD. - All completed features are integrated and do not break the full system.​ - Architectural guidelines are respected.​ - Full Docker Compose setup starts without errors:​ ○​OpenSearch + Dashboards​ ○​Load Generator​ ○​Metrics Reporter / Metrics Storage (if present)​ ○​Report Controller​ ○​Logging stack (Promtail/Loki) if used​○​Metrics Reporter / Metrics Storage (if present)​ - The increment can be demonstrated in the Sprint Review without failures. | - All required scenarios implemented and automated. - Reproducible runs produce archived results (raw + aggregated charts). - Required performance/resilience targets met for mandatory scenarios. - Documentation is complete (test plan, runbook, interpretation guide, reproducibility checklist). - No open critical bugs. - All promised components implemented:​ ○​Fully working Load Generator​ ○​Query Execution + Templates​ ○​Metrics Reporter​ ○​Report Controller (prototype level is OK if IP handles the rest)​ ○​Stable OpenSearch integration​ ○​Data generation for “ano” and “duo”​ - Final code review approved by the team.​ - No critical warnings or dead code.​ - Repository clean with no unmerged branches.​
Tests & Validation | - Unit tests: new/changed classes covered (place under module src/test/java). - Integration test: Testcontainers or short docker-compose integration that exercises the feature against OpenSearch. - Smoke run: a short end‑to‑end scenario (e.g., 30–60s) that demonstrates feature behavior and produces output. - Basic manual testing completed.​ - Logs checked and no unexpected errors appear.​ - Code review completed and approved by at least one teammate.​ - DTOs, controllers, YAML config files updated as needed | (- Run the sprint acceptance scenarios: population → run → collect → validate.) (- Validation scripts assert basic pass/fail (no critical errors, p95/p99 within sprint thresholds).) All commits pass CI:​ ○​Build​ ○​Unit tests​ ○​Static analysis (lint)​ ○​Formatting​ - No critical errors in logs.​ | - Full end-to-end validation runs executed (including at least one soak and one chaos test) and validated by scripts. - Regression/reproducibility check: repeat a representative scenario and verify results within accepted variance (e.g., ±10%). - Unit + integration suites green. - Docker Compose environment stable and reproducible.​ - Entire stack starts from scratch without errors.​ - Final load tests executed and documented.​ - ​Logs structured and free of critical problems.​ - Final demonstration with DATEV/IP completed.​ - Test coverage includes:​ ○​Happy-path scenarios​ ○​Error handling (e.g., OS down, timeout, invalid configs, multi-threading)​ - Minimal stress tests documented.​
Documentation | - Usage example added to module README.md and/or wiki. | - Sprint notes updated in the wiki.​ - Architecture diagrams updated if anything changed.​ - API documentation updated with new endpoints.​ | - Deliverables/ contains final reports, scenario definitions, scripts to reproduce, dashboard exports and a README with exact reproduction commands. - Documentation/ contains runbook, interpretation guide, and troubleshooting steps, final architecture​, docker setup​, API endpoints​, execution examples​, "How to add new queries​", "how to generate and upload data to OpenSearch​" as part of wiki. - Final presentation delivered
CI / Automation (when existing) | - PR CI must run build + unit tests + linter. - Integration smoke test recommended in merge pipeline (if it’s fast); otherwise on main/merge job. | - Merge/main pipeline runs smoke acceptance scenarios (short) or a job that can be manually triggered to run them. - CI artifacts for the sprint (result JSON/CSV and summary) are archived in pipeline artifacts. | - Release pipeline builds artifacts (JARs, Docker images) and archives results. - Nightly or release-run perf jobs executed and artifacts persisted; CI flags regressions compared to baselines. - Dependency/security scans completed.
Metrics & Thresholds | - If performance-related: attach baseline and verify no significant regression (>10% on critical metric) unless approved. - Smoke validation: error rate < 5% (adjustable per scenario) and p95 reported. PR Checklist - Issue/story linked - Unit tests added + passing - Integration/smoke test added - Documentation updated - Reviewer approved | - Sprint acceptance thresholds defined per scenario (e.g., for that sprint: p95 <= 600 ms, error rate <= 2%). - If thresholds not met, the sprint cannot be marked finished until remediation or explicit acceptance by PO. PR Checklist - All sprint issues linked and merged - Acceptance scenarios included and runnable - Deliverables/sprint-XX populated with results - CI artifacts archived - PO/TA acknowledged | - Project-level mandatory thresholds must be met (define concretely before final validation, e.g.): - Steady-state p95 <= X ms, p99 <= Y ms, error rate <= Z%. - Soak: sustained stability for N minutes without memory growth or node crashes. - Chaos: cluster remains available and recovers within R minutes. - Reproducibility: repeated runs within ±10% of throughput and latency targets (tunable). PR / Release Checklist - All scenarios automated and in repo - Deliverables folder contains final reports and artifacts - Release build artifacts created (JARs, Docker images) - Baselines and comparison scripts in place - Security/dependency checks done - PO/TA and technical reviewers sign off
Sign-off | At least one technical reviewer; feature owner or PO must approve if feature affects user behavior or public interfaces. | Product Owner acceptance of sprint deliverables and at least one technical reviewer sign-off. | Formal sign-off by Product Owner / Teaching Assistant and at least two technical reviewers; release tagged and artifacts archived.

## Documentation
Type | Link / reference
Wiki | https://github.com/amosproj/amos2025ws01-opensearch-load-tester/wiki

## Bill of Materials
# | Context | Name | Version | License | Comment
1 | environment | Eclipse Temurin OpenJDK | 25 (LTS) | GPL-2.0 with Classpath Exception | Java runtime used for building and running the application
2 | environment | Docker | 28.5.1 | Apache-2.0 | Container environment for running OpenSearch and Load Tester services
3 | tool | Apache Maven | 3.9.11 | Apache-2.0 | Build automation and dependency management tool
4 | library | spring-boot-starter | 3.5.7 | Apache-2.0 | Entry point for Spring Boot dependency management
5 | library | spring-boot | 3.5.7 | Apache-2.0 | Core framework providing auto-configuration and runtime support
6 | library | spring-context | 6.2.12 | Apache-2.0 | Dependency injection and application context management
7 | library | spring-aop | 6.2.12 | Apache-2.0 | Aspect-oriented programming support
8 | library | spring-beans | 6.2.12 | Apache-2.0 | Bean creation and configuration framework
9 | library | spring-expression | 6.2.12 | Apache-2.0 | Spring Expression Language (SpEL) processing
10 | library | spring-boot-autoconfigure | 3.5.7 | Apache-2.0 | Automatically configures components based on classpath
11 | library | spring-boot-starter-logging | 3.5.7 | Apache-2.0 | Default logging configuration using Logback
12 | library | logback-classic | 1.5.20 | EPL-1.0 | Logging backend implementing SLF4J API
13 | library | logback-core | 1.5.20 | EPL-1.0 | Core utilities for Logback logging
14 | library | log4j-to-slf4j | 2.24.3 | Apache-2.0 | Redirects Log4j 2 logs to SLF4J
15 | library | jul-to-slf4j | 2.0.17 | MIT | Bridges java.util.logging to SLF4J
16 | library | jakarta.annotation-api | 2.1.1 | EPL-2.0 | Jakarta annotations used by Spring components
17 | library | spring-core | 6.2.12 | Apache-2.0 | Core utilities and classloading framework of Spring
18 | library | spring-jcl | 6.2.12 | Apache-2.0 | Logging abstraction used internally by Spring
19 | library | snakeyaml | 2.4 | Apache-2.0 | YAML parser for configuration files
20 | library | micrometer-core | 1.15.5 | Apache-2.0 | Core metrics collection API
21 | library | micrometer-commons | 1.15.5 | Apache-2.0 | Shared utilities for metrics instrumentation
22 | library | micrometer-observation | 1.15.5 | Apache-2.0 | Captures timing and observation data for metrics
23 | library | HdrHistogram | 2.2.2 | CC0-1.0 | High-resolution latency measurement library
24 | library | LatencyUtils | 2.0.3 | CC0-1.0 | Helper utilities for latency tracking
25 | library | micrometer-registry-prometheus | 1.15.5 | Apache-2.0 | Exposes Micrometer metrics to Prometheus
26 | library | prometheus-metrics-core | 1.3.10 | Apache-2.0 | Core Prometheus metrics collection
27 | library | prometheus-metrics-model | 1.3.10 | Apache-2.0 | Data model for Prometheus metrics
28 | library | prometheus-metrics-config | 1.3.10 | Apache-2.0 | Configuration utilities for Prometheus metrics
29 | library | prometheus-metrics-tracer-common | 1.3.10 | Apache-2.0 | Common tracing utilities for Prometheus exporters
30 | library | prometheus-metrics-exposition-formats | 1.3.10 | Apache-2.0 | Serialization formats for Prometheus metrics
31 | library | prometheus-metrics-exposition-textformats | 1.3.10 | Apache-2.0 | Text exposition format for Prometheus
32 | library | lombok | 1.18.34 | MIT | Generates boilerplate code (getters/setters, builders, etc.)
33 | library | opensearch-rest-high-level-client | 2.16.0 | Apache-2.0 | REST client for interacting with OpenSearch clusters
34 | library | opensearch | 2.16.0 | Apache-2.0 | Core OpenSearch library
35 | library | opensearch-common | 2.16.0 | Apache-2.0 | Common interfaces and utilities for OpenSearch modules
36 | library | opensearch-core | 2.16.0 | Apache-2.0 | Core APIs for OpenSearch operations
37 | library | opensearch-compress | 2.16.0 | Apache-2.0 | Compression utilities used internally by OpenSearch
38 | library | zstd-jni | 1.5.5-5 | BSD-2-Clause | Java bindings for Zstandard compression
39 | library | opensearch-secure-sm | 2.16.0 | Apache-2.0 | Security manager integration for OpenSearch
40 | library | opensearch-x-content | 2.16.0 | Apache-2.0 | Serialization/deserialization utilities in OpenSearch
41 | library | jackson-dataformat-smile | 2.19.2 | Apache-2.0 | Jackson module for Smile binary JSON
42 | library | jackson-dataformat-cbor | 2.19.2 | Apache-2.0 | Jackson module for CBOR binary JSON
43 | library | opensearch-geo | 2.16.0 | Apache-2.0 | Geospatial data and query support for OpenSearch
44 | library | opensearch-telemetry | 2.16.0 | Apache-2.0 | Telemetry and monitoring features for OpenSearch
45 | library | lucene-core | 9.11.1 | Apache-2.0 | Core search and indexing engine powering OpenSearch
46 | library | lucene-analysis-common | 9.11.1 | Apache-2.0 | Text analysis and tokenization utilities
47 | library | lucene-backward-codecs | 9.11.1 | Apache-2.0 | Backward-compatible codecs for old Lucene versions
48 | library | lucene-grouping | 9.11.1 | Apache-2.0 | Implements result grouping and field collapsing
49 | library | lucene-highlighter | 9.11.1 | Apache-2.0 | Highlighting support for search result snippets
50 | library | lucene-join | 9.11.1 | Apache-2.0 | Supports join queries between documents
51 | library | lucene-memory | 9.11.1 | Apache-2.0 | In-memory index structures for fast search
52 | library | lucene-misc | 9.11.1 | Apache-2.0 | Miscellaneous utilities and experimental features
53 | library | lucene-queries | 9.11.1 | Apache-2.0 | Advanced query utilities and filters
54 | library | lucene-queryparser | 9.11.1 | Apache-2.0 | Parses textual queries into Lucene queries
55 | library | lucene-sandbox | 9.11.1 | Apache-2.0 | Experimental Lucene modules
56 | library | lucene-spatial-extras | 9.11.1 | Apache-2.0 | Spatial/geographic query utilities
57 | library | lucene-spatial3d | 9.11.1 | Apache-2.0 | 3D geospatial shapes and indexing
58 | library | lucene-suggest | 9.11.1 | Apache-2.0 | Suggestion/autocomplete engine
59 | library | opensearch-cli | 2.16.0 | Apache-2.0 | Command-line tools for OpenSearch management
60 | library | jopt-simple | 5.0.4 | MIT | Command-line option parser
61 | library | joda-time | 2.12.7 | Apache-2.0 | Date and time handling library
62 | library | t-digest | 3.2 | Apache-2.0 | Statistical distribution estimation for percentiles
63 | library | log4j-api | 2.24.3 | Apache-2.0 | Core Log4j 2 API
64 | library | log4j-jul | 2.24.3 | Apache-2.0 | Bridge for Java Util Logging to Log4j
65 | library | jna | 5.13.0 | LGPL-2.1-or-later OR Apache-2.0 | Java Native Access for system-level operations
66 | library | jzlib | 1.1.3 | BSD-4-Clause | Java implementation of zlib compression
67 | library | reactor-core | 3.7.12 | Apache-2.0 | Reactive programming support (Project Reactor)
68 | library | reactive-streams | 1.0.4 | MIT-0 | Minimal reactive streams specification
69 | library | protobuf-java | 3.22.3 | BSD-3-Clause | Google Protocol Buffers serialization
70 | library | opensearch-rest-client | 2.16.0 | Apache-2.0 | Low-level REST client for OpenSearch
71 | library | httpclient | 4.5.14 | Apache-2.0 | Apache HTTP client for network communication
72 | library | httpcore | 4.4.16 | Apache-2.0 | Core transport components for Apache HTTP client
73 | library | httpasyncclient | 4.1.5 | Apache-2.0 | Asynchronous HTTP client for non-blocking I/O
74 | library | httpcore-nio | 4.4.16 | Apache-2.0 | NIO transport layer for asynchronous HTTP
75 | library | commons-codec | 1.18.0 | Apache-2.0 | Utility library for encoding/decoding formats
76 | library | commons-logging | 1.2 | Apache-2.0 | Lightweight logging abstraction
77 | library | mapper-extras-client | 2.16.0 | Apache-2.0 | Additional mapping features for OpenSearch
78 | library | parent-join-client | 2.16.0 | Apache-2.0 | Supports parent-child relationships in OpenSearch
79 | library | aggs-matrix-stats-client | 2.16.0 | Apache-2.0 | Advanced aggregation statistics module
80 | library | rank-eval-client | 2.16.0 | Apache-2.0 | Ranking evaluation tools for OpenSearch
81 | library | lang-mustache-client | 2.16.0 | Apache-2.0 | Template rendering support (Mustache)
82 | library | compiler | 0.9.14 | Apache-2.0 | Annotation processing and compilation utilities
83 | library | jackson-dataformat-yaml | 2.19.2 | Apache-2.0 | YAML serialization and deserialization
84 | library | jackson-databind | 2.19.2 | Apache-2.0 | Object–JSON mapping framework
85 | library | jackson-annotations | 2.19.2 | Apache-2.0 | Annotations for Jackson serialization/deserialization
86 | library | jackson-core | 2.19.2 | Apache-2.0 | Core streaming JSON processor
87 | library | slf4j-api | 2.0.17 | MIT | Unified logging abstraction layer

## Planning Poker
Last Name | First Name | Value
Lorenz | Alexander | 5 | 5 | OK
Buchner | Lea | 5
Engelhard | Dirk
Strachwitz | Carlo
Belz | Sara |  | 0 | No size
Becker | Eugen |  | 1 | Trivial size
Hofmann | Leo |  | 2 | Small size
Knecht | Sebastian |  | 3 | Medium size
|  |  | 5 | Large size
|  |  | 8 | Very large size
|  |  | 13 | Too large (size)
How to play planning poker
1. Everyone type their number into their value field, don't hit return yet
2. Someone, perhaps a product owner, count down 3.. 2.. 1..
3. Then, everyone hit return to submit their value